## Slide 1: CPP Annual Plan 2024-25 6-month review
Helen Murphy
Associate Programme Director CPP
6th December 2024

## Slide 2
Clinical Pathways Leadership Team
T&O
ENT
Dermatology
Gynaecology
Cardiology
CPP Specialties
General Surgery
Urology
Ophthalmology
MSK
Perioperative
Children & Young People
Supported Clinical Networks
Clinical Pathways Programme Overview
Elective Recovery & Clinical Pathways Programme Board
Notes: Size of waiting lists, workforce and sustainability

## Slide 3
Clinical Pathways Programme Ambitions
Patient Centred
Sustainable
Innovative
Improving patient experience and outcomes, and reducing inequalities in care
Developing service models that are resilient and fit for the future
Harnessing new technologies and innovations to improve care and productivity

## Slide 4: Ophthalmology
Notes: R

## Slide 5: 24/25 workplan
Implement Single Point of Access Pilot
Implement Glaucoma Monitoring Service Pilot
Implement Advice and Guidance Pilot
Explore opportunities for Glaucoma Enhanced Case Finding Service
£475k NHSE Eyecare Accelerator Round 1 funding
£300k NHSE transformation funding
£207k NHSE Eyecare Accelerator Round 2 funding + £200k NHSE transformation funding
On track
Launched 1st July 2024
Ongoing management and monitoring of pilot
Delayed Q1/2 progress
Due to launch 1st April 2025
Contract variation underway
On track
Funding received to pilot
Procurement process underway
On track
Launched across Sept and Nov 2024
Ongoing management and monitoring of pilot
Unfunded – Trust’s voluntarily participating

## Slide 6: Key achievements Q1/Q2
ECHT
COCH
WHH
Launched single point of access pilot
Triage for all ophthalmology referrals
East Cheshire, West Cheshire, St Helens, Halton and Knowsley
6-month pilot with option to extend for further 6 months
Contract awarded to Primary Eyecare Services
Launched advice and guidance pilot
ECHT, MCHT, COCH and selected optometry practices across Cheshire.
Network development
Re-launched network in January 2024
Strong clinical leadership
Representation from secondary care, primary care and ICB
Individual task and finish groups established for programmes of work
Cataract pathway visits completed at:
WUTH
LUHFT
Chart: 
 | 5.8 | 2.6 | 6.1 | 5.7 | 79.8
242
returned for additional information
110
rejected as not required
255
diverted to primary care service
Identified 237
additional referrals that could have been diverted to Glaucoma Enhanced Case Finding service
4175
referrals
triaged
July-September 24
Glaucoma Services
Successful bid for funding to implement Glaucoma Enhanced Case Finding Service across C&M
Contract variation underway for implementation of Glaucoma Monitoring Service across C&M
Patient outcomes and experience
Mrs N was seen by an optometrist for her first sight test in the UK and was referred routinely to secondary care for a second opinion.
Referral was picked up within the SPoA triaging team and deemed suitable for CUES with an OCT scan for further investigation.
The second optometrist noted very high intraocular pressures which allowed them to make a tailored urgent referral to the glaucoma clinic.
This saved the patient waiting for a routine appointment on a long waiting list and potentially saved the patient some sight, as glaucoma is a progressive disease.
This triaging, reassessment and reclassification of urgency has meant the patient was identified as needing urgent treatment and was aptly referred onwards for this.

## Slide 7: Gynaecology

## Slide 8: 24/25 workplan
Menopause – Phase 1 Pilot between LWH & Liverpool Central PCN
Menopause – Phase 2 Pilot between LWH & Sefton PCN
Pelvic Pain – Timely access to ultrasound – CDC pilot
Reason for Referral – Provider Audit
Unfunded – collaboration between LWH & Lliverpool Central PCN - agreed SLA
Unfunded – collaboration between LWH & Sefton PCN – agreed SLA
Business As Usual
Launched April 2024 for 6 months
Continued agreed provision of community appointments
Learning and outcomes applied to ‘Phase 2’ planning
Planning – On Track
Due to launch January 2025 for 6 months
Applied learning from Phase 1
Reduce demand on LWH (alongside Phase 1 created capacity)
On track
Due to conclude in November 2024
Recommendations to be formally shared in December 2024
Outcomes to shape 25/26 workplan
Planning – On Track
Due to launch Jan/Feb 2025
Improve time to wait to USS for GP Direct Referrals as recommended by GIRFT / CQC
Capacity submission as part of profiling for CDCs in Sept 2024
£5k funding from Elective Recovery

## Slide 9: Key achievements Q1/Q2
Participation from;
Mersey West Lancs (Whiston & S&O),Wirral, Warrington and Liverpool Womens
Menopause Phase 1 & Phase 2 Pilots
Scope/Context:
BMS trained GPs delivering community-based Menopause clinics for non-complex LWH patients – waiting longer than acceptable on acute waiting lists
Creation of acute based capacity to support complex Menopause waiting lists, other challenged specialities or mutual aid requests.
Mutually beneficial contract arrangements; LWH claim the appointment tariff and pay the PCN per appointment attended at a rate competitive with LARC.
Risk addressed through ongoing LWH clinical oversight and mentorship.
Launched reason for referral audit
Network Development
Monthly CPP updates to Gynaecology Network; progress against agreed PID.
Engagement with providers across C&M to support with local initiatives to support long term transformation and achieving Elective Recovery targets
Ongoing positive engagement with Network Leadership
Expected targets for Phase 1/Phase 2 – to be achieved by June 25
*Awaiting final community capacity to finalise targets
Invited to present to Department of Health in Oct 2024 – LWH lead and CMAST Programme Manager
Launched performance and piloted benefit dashboard
Benefit dashboard designed and built to track key metrics monthly
Performance dashboard designed and launched in Oct 24 – rolling programme of focus for Jan – Dec 25 outlined
Create
55-130
appt slots per month across locations*
Reduce waiting times for new appointments to 12WW*
Clinics to include new patients and follow ups
Focused approach to reducing DNA rate as care closer to home
Creation of acute based capacity to support complex Menopause waiting lists, other challenged specialities or mutual aid requests.

## Slide 10: Ear, Nose and Throat

## Slide 11: 24/25 workplan
Single Electronic Referral System for C&M ENT
Strategic discussions – improved sustainability
Audiology pathways
In progress with some delays
Draft project brief defined and circulated
Aligning plans to launch against ICB/national ambitions
Planning – On Track
Strategic Directors presentation in Oct 2024
Strategy options discussion in November 2024
Planning – On Track
Changes to GP referrals completed at COCH
Piloting single triage system for Audiology irrespective of age – support to reduce waiting times
Outcomes and recommendations due in Jan 2025

## Slide 12: Key achievements Q1/Q2
Menopause Phase 1 & Phase 2 Pilots
Network Development
Ongoing strong Network Leadership from Clinical Lead and Medical Director
Relaunch of Network in April 2024
Agreed priorities set against Further Faster recommendations
Strategic discussions for long term system resilience have begun
*Awaiting final community capacity to finalise targets
Achieved reduction and managing DNAs checklist
C&M ENT currently achieving national value of 8%
Local initiatives to reduce further to come under national value
Achieved PIFU national value
C&M ENT currently exceeding national value for PIFU
(C&M achieving 6.6% against 5.2% national value)
Network workstream working on a single approach to ENT PIFU
Improving Audiology pathways
Countess of Chester piloting changes to GP referral form to Audiology; lowering age threshold to 18 years
Set to improve waiting times for Audiology patients 18-49 years old otherwise waiting longer than 50+ due to pathway
Outcomes due to ENT Network in January 2025
A single Electronic Referral System for ENT
Baselining of current referral processes across C&M completed
Aiming to achieve a single approach to referral management;
National eRS team have agreed to support this work

## Slide 13: Dermatology

## Slide 14: 24/25 workplan
Procure a single unified teledermatology solution for C&M
Current Goal: C&M implementation of AI into dermatology 2WW pathway
On Hold
Service Specification - completed
Pre-market engagement – completed
Full procurement put on hold whilst the benefits of Skin Analytics are being assessed
Require a C&M direction of travel for a single eRS
Planning – On Track
4 Trusts across C&M in planning stage for implementation
1 trust live and 1 trust re-evaluating pathway to increase numbers
Expected go-live dates of Jan 2025

## Slide 15: Key achievements Q1/Q2
ECHT
COCH
WHH
Trusts signed up to the implementation of AI
WUTH
MWL
MCT
CoC
BW (Bridgewater)
LUHFT (ongoing pilot)
Focus is on the implementation of artificial intelligence on the 2WW suspected cancer pathway to reduce unnecessary face to face appointments and free up clinical capacity for long waiters on the inflammatory conditions pathway, successful EOI to NHSE for the value of £1m
Pre EOI Success
Prior to NHSE expression of interest success LUHFT had been successful in a bid for funding for their own AI pilot with Skin Analytics
LUHFT not included in the CMAST funding but are working closely with CMAST to ensure a streamlined approach across C&M
To minimise unnecessary face to face appointments​
To consistently achieve 28-day FDS skin cancer target​
All appropriate trusts live with Skin Analytics​
Reduce the number of urgent suspected skin cancer F2F app for trusts implementing telederm element​
Funding Success
CMAST CPP have been successful in a EOI bid for 12 months funding for 5 out of 6 trusts across C&M to implement an Artificial Intelligence Software
Totalling - £997,735
Expected Benefits
To discharge >30% of urgent (USSC) teledermatology skin cancer patients without relying on trust clinician capacity
80% of patients told cancer or no cancer within 28 days​
80% of patients reviewed by a dermatologist within 14 days of referral
Min 75% patients seen at an imaging app within 7 working days​
80% (minimum) of urgent suspected cancer referrals going through the Skin Analytics service​
70% avoidance of urgent appointments utilising the Skin Analytics Teledermatology element.

## Slide 16: Cardiology

## Slide 17: 24/25 workplan
Define Clinical Pathway Improvement Opportunities for C&M
Data Collection and Options Analysis
C&M Cardiac Cath Lab Options Appraisal
Business Case Development & Implementation Planning
Output: Agreement to prioritise the strategy for Cath Lab Provision
Output: 4 potential options agreed for C&M
Next steps dependent on outcome of Business Case Approval
Delivered Q1
Incorporation of GIRFT Recommendations / BCIS Guidance
Strategic Workshop held in April 24 to define / prioritise work for Cardiology Provider Alliance
Delivered Q2-Q3
Data collection to understand current diagnostic & treatment services across Cath Labs
Data modelling aided the development of potential options for future provision
On track for Q4
Sub-groups for Cardiac Pacing / Cardiac Imaging established
Governance process for ICB approval in progress
Delivered Q2-Q3
Define change implications / considerations (Quality, Safety, Equity, Experience, Finance, Workforce & Estate)
2 Options Appraisal workshops Delivered: 24th September / 4th November
Output: 2 Options Shortlisted for review at Cardiology Provider Alliance / CPP Core Leadership Group Meeting

## Slide 18: Key achievements Q1/Q2
LHCH
COCH
WHH
C&M Cath Lab Strategy
Key Objectives
Objective 1 – Ensure all invasive angiograms are undertaken on PCI capable Cath Lab sites, by PCI trained operators.
Objective 2 – Ensure investigation of chest pain is undertaken following NICE guidance i.e. non-invasive tests where applicable.
Cardiology Provider Alliance Mission
Incorporate GIRFT recommendations to improve the C&M chest pain pathway, with the aim to better utilise diagnostic and treatment services across Catheter Labs; whilst maximising the utilisation of non-invasive diagnostic alternatives.
Current C&M Provision of Cath Lab Services:
WUTH
MWL
LUHFT
Scope:
Cardiac Cath Lab Provision (Diagnostic Coronary Angiography & PCI)
Provision of non-invasive imaging
Delivery of pacing services
Governance
Cardiology Provider Alliance – Strategic Steering Group
Chair; Dr John Morris - Divisional Medical Director, LHCH
Cardiac Imaging – Tactical Working Group
Cardiac Pacing –Tactical Working Group
Expected Benefits:
Improved Resource Utilisation
Enhanced Patient Experience
Improved Compliance with NICE / BCIS Guidance
Reduction in Duplicate Tests
[Up to 250 per year]
Reduction in Unnecessary Invasive Procedures
[Between 500-600 per year]
Provider Alliance Established in April 2024
Representation from every Trust with Cardiac Services across C&M
Strong clinical leadership
Individual task and finish groups established for Pacing & Imaging